## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 |  |  | Semantic retrieval returned less relevant evidence for some queries | Sprint 1 | Abhik | Functional | Refined chunking strategy and retrieval parameters to improve relevance. | 2026-07-07 | Closed | Verified using multiple test queries.
2 |  |  | Frontend could not communicate with backend APIs due to CORS configuration | Sprint 1 | Abhik | Integration | Configured CORS middleware and validated API communication. | 2026-07-10 | Closed | Frontend and backend integrated successfully.
3 |  |  | Hallucination Judge assigned scores when supporting evidence was unavailable | Sprint 1 | Abhik | Logic | Implemented INSUFFICIENT_EVIDENCE handling instead of assigning misleading scores. | 2026-07-17 | Closed | Improved evaluation reliability and avoided false hallucination penalties.
4 |  |  | Frontend did not support the new hallucination evaluation status | Sprint 1 | Abhik | UI | Updated the evaluation dashboard to display "Not Evaluated" for insufficient-evidence cases. | 2026-07-18 | Closed | UI now correctly handles insufficient-evidence outcomes.
5 |  |  | Structured LLM responses occasionally failed schema validation | Sprint 1 | Abhik | Validation | Strengthened Pydantic validation and standardized structured JSON output handling. | 2026-07-19 | Closed | Structured judge responses validated successfully during testing.
6 |  |  | Minor issues identified during end-to-end testing | Sprint 1 | Abhik | Testing | Fixed identified defects and completed regression testing. | 2026-07-20 | Closed | Initial Milestone 2 test suite completed successfully.
7 |  |  | Completeness evaluation required an independent scoring approach | Sprint 2 | Abhik | Logic | Implemented a dedicated Completeness Judge with separate scoring criteria and structured output. | 2026-07-25 | Closed | Completeness remains independent from Relevance, Accuracy, and Hallucination.
8 |  |  | Final verdict required consistent combination of multiple judge results | Sprint 2 | Abhik | Logic | Implemented deterministic weighted Verdict scoring using Accuracy, Completeness, Relevance, and Hallucination dimensions. | 2026-07-27 | Closed | Final score is calculated deterministically rather than relying on another LLM score.
9 |  |  | Batch CSV files required validation for different input structures | Sprint 2 | Abhik | Validation | Implemented CSV schema validation, required-field checks, optional reference-answer handling, and invalid-row handling. | 2026-07-30 | Closed | Invalid batch input is rejected before evaluation.
10 |  |  | Processing every batch row independently caused excessive model calls | Sprint 2 | Abhik | Performance | Implemented grouped batch processing so multiple records can be evaluated in fewer Gemini requests. | 2026-08-01 | Closed | Improved batch efficiency while preserving individual evaluation results.
11 |  |  | Digital QA PDF input required additional parsing support | Sprint 2 | Abhik | Functional | Extended the batch pipeline to parse structured PDF question-answer data and integrate it with the evaluation workflow. | 2026-08-02 | Closed | PDF/Digital QA batch workflow verified.
12 |  |  | Users had limited visibility into long-running batch processing | Sprint 2 | Abhik | UI | Implemented batch progress tracking with processing status and completion information. | 2026-08-03 | Closed | Users can monitor batch execution progress.
13 |  |  | Batch results were difficult to inspect across multiple evaluations | Sprint 2 | Abhik | UI | Implemented batch statistics, result tables, search, filtering, and evaluation summaries. | 2026-08-05 | Closed | Batch results are now easier to analyze and review.
14 |  |  | Batch reports did not initially contain all required evaluation information | Sprint 2 | Abhik | Reporting | Refined batch PDF/CSV reporting to include dimension scores, overall verdicts, and evaluation summaries. | 2026-08-06 | Closed | Reporting workflow verified with generated output.
15 |  |  | Dashboard did not initially provide all required Milestone 4 analytics | Sprint 3 | Abhik | Functional | Audited the existing dashboard and implemented analytics for total evaluations, dimension averages, verdict distribution, hallucination statistics, and trends. | 2026-08-10 | Closed | Dashboard aligned with Milestone 4 scoring requirements.
16 |  |  | Dashboard needed visual analytics for easier interpretation | Sprint 3 | Abhik | UI | Added dimension score, verdict distribution, and quality trend visualizations. | 2026-08-12 | Closed | Charts verified with analytics data.
17 |  |  | Hallucination analytics initially needed clearer separation of insufficient evidence | Sprint 3 | Abhik | Logic | Separated grounded, hallucinated, and insufficient-evidence populations in the analytics calculations. | 2026-08-13 | Closed | Insufficient-evidence cases are not incorrectly counted as hallucinations.
18 |  |  | Analytics required filtering across different evaluation subsets | Sprint 3 | Abhik | Functional | Implemented filters for date range, evaluation mode, verdict, and model metadata where available. | 2026-08-15 | Closed | Filtered analytics correctly reflect the selected evaluation population.
19 |  |  | Single evaluation analytics showed missing dimension scores | Sprint 3 | Abhik | Data Persistence | Traced the data flow from judge output through the HistoryMapper and fixed persistence so all individual judge results are stored. | 2026-08-16 | Closed | Relevance, Accuracy, Hallucination, Completeness, and Verdict results are now preserved for new evaluations.
20 |  |  | Legacy evaluations contained only summary verdict information | Sprint 3 | Abhik | Data Integrity | Added summary-only handling so missing historical dimension scores are not fabricated or displayed as zero. | 2026-08-16 | Closed | Legacy records are explicitly treated as summary-only.
21 |  |  | Batch PDF lacked dedicated hallucination analysis and recommendations | Sprint 3 | Abhik | Reporting | Added Hallucination Analysis and Improvement Recommendations sections based on actual batch evaluation results. | 2026-08-17 | Closed | Final batch PDF contains all required reporting sections.
22 |  |  | Authentication verification links redirected to localhost during deployment | Sprint 3 | Abhik | Configuration | Updated Supabase Site URL and allowed redirect URLs to use the deployed Vercel frontend. | 2026-08-18 | Closed | Email verification and OAuth redirects work with the production deployment.
23 |  |  | Frontend routes returned 404 when refreshed on Vercel | Sprint 3 | Abhik | Deployment | Added SPA rewrite configuration so client-side React routes resolve correctly after refresh. | 2026-08-18 | Closed | Evaluator, History, and other frontend routes refresh correctly.
24 |  |  | Uptime monitoring returned 405 for the backend health endpoint | Sprint 3 | Abhik | Deployment | Updated the health endpoint to accept both GET and HEAD requests used by monitoring services. | 2026-08-18 | Closed | UptimeRobot health monitor reports the backend as Up.
25 |  |  | Final system required complete regression verification across backend and frontend | Sprint 3 | Abhik | Testing | Executed backend tests, frontend build and lint verification, analytics checks, persistence checks, PDF generation, and production workflow tests. | 2026-08-18 | Closed | Latest documented verification recorded 163 backend tests passed, frontend build passed, lint had 0 errors, and batch PDF generation passed.